YCAP- GenAI

Case-

"ABC Infrastructure Ltd. ABC Infrastructure Ltd. manages multiple construction projects involving large quantities of cement, steel, sand, aggregates, tiles, electrical materials, and other construction materials. During recent projects, the company has experienced increases in material costs, unexpected delivery delays, and variations between planned and actual expenditure. These issues are affecting project budgets and overall profitability. You have been hired as an AI-powered Construction Cost Analyst. Your responsibility is to analyze historical material procurement data, identify cost overruns and vendor-related issues, and provide recommendations for better cost and material management. "

Dataset-

https://docs.google.com/spreadsheets/d/1tKhKRCGR8CBlRuE_v2vmPz5D3X3rM2qtVj1uhuG8khE/edit?gid=1493405022#gid=1493405022

Questions-

1. The CEO wants a quick overview before the board meeting.

2. Management believes that a variety of factors are delaying the project. List out the major reasons.

3. Which vendors/ aspects are causing no delay or are working before schedule?

4. Do the major delay causing aspects have any available alternative that can help bring the project to the scheduled timeline?

5. Can rescheduling/ reshuffling of any activities lead to a better achieved timeline?

6. Are the "on time" or "Before time" aspects causing clashes in workings of the site which are probably causing unnecessary delays?

7. What measures are being taken to battle the delays in the project?

8. How much of the delay is being caused by uncontrollable factors such as environmental hinderance?

- Can any of the delays be avoided/ countered by hiring extra manpower/ machinery?

10. Are any of the delays being caused due to lack of funds, material or inadequate inventory?

Answers (GenAI)-

1. CEO Quick Overview (Board Meeting Summary)

Schedule Variance: Out of 100 procurement orders, 80% experienced delivery delays, accumulating 538 total delay days across projects (averaging 6.72 delay days per delayed order).

Cost Variance: Total procurement expenditure escalated from a planned ₹9.70 Crore to an actual ₹10.11 Crore, resulting in an overall cost overrun of ₹40.67 Lakhs (+4.19%).

Primary Bottlenecks: Delays are heavily concentrated in Sand (33.5% of total delays), Plumbing (20.6%), and Steel (18.6%).

Operational Bright Spots: Ready Mix Concrete (Synergy Concrete Co) and Aggregates (Apex Aggregates) achieved 100% on-time delivery (0 delay days) and zero cost overruns.

2. Major Delay Factors & Breakdown

MAJOR CAUSES OF DELIVERY DELAYS

(Total Delay Days Across 100 POs)

Quarry Restriction   |========================================== 180 days (33.5%)

Transport Strike     |=========================== 111 days (20.6%)

Production Backlog   |======================== 100 days (18.6%)

Logistics Delay      |================ 66 days (12.3%)

Raw Material Shortage|========= 35 days (6.5%)

Customs Delay        |====== 25 days (4.6%)

Weather Delay        |=== 12 days (2.2%)

Minor Transit Hold   |* 1 day (0.2%)

| Delay Reason | Delayed Orders | Total Delay Days | % of Total Delays | Avg Delay (Days) | Financial Impact (Cost Variance) |
| --- | --- | --- | --- | --- | --- |
| Quarry Restriction | 15 | 180 | 33.5% | 12.0 | +₹19,19,100 |
| Transport Strike | 9 | 111 | 20.6% | 12.3 | +₹28,300 |
| Production Backlog | 13 | 100 | 18.6% | 7.7 | +₹12,95,000 |
| Logistics Delay | 17 | 66 | 12.3% | 3.9 | +₹5,01,700 |
| Raw Material Shortage | 7 | 35 | 6.5% | 5.0 | +₹1,25,500 |
| Customs Delay | 5 | 25 | 4.6% | 5.0 | +₹1,09,000 |
| Weather Delay | 6 | 12 | 2.2% | 2.0 | +₹1,79,000 |
| Minor Transit Hold | 1 | 1 | 0.2% | 1.0 | -₹20,000 |

3. On-Time & Exemplary Vendor Performance

Two major supply categories and vendor partnerships are operating with zero schedule slippage:

| Vendor Name | Material Category | PO Count | Delay Days | Vendor Rating | Defective Units | Cost Variance |
| --- | --- | --- | --- | --- | --- | --- |
| Synergy Concrete Co | Concrete (RMC M25, M30, M35, M40) | 10 | 0 Days | 4.8 / 5.0 | 0 | ₹0 |
| Apex Aggregates | Aggregates (Blue Metal, Gravel, Dust) | 10 | 0 Days | 4.5 / 5.0 | 0 | ₹0 |

4. Strategic Alternatives for Major Bottlenecks

+------------------------------------------------------------------------------------+

|                         BOTTLENECK VS ALTERNATIVE STRATEGY                         |

+--------------------+-----------------------+---------------------------------------+

| Bottleneck         | Root Cause            | Recommended Viable Alternative        |

+--------------------+-----------------------+---------------------------------------+

| Sand               | Quarry bans & legal   | Transition to Manufactured Sand       |

| (180 delay days)   | permits               | (M-Sand) & Crushed Stone Wash Plants  |

+--------------------+-----------------------+---------------------------------------+

| Plumbing           | Single-vendor transit | Dual-source via regional distributors |

| (111 delay days)   | strikes               | with local warehouse stock            |

+--------------------+-----------------------+---------------------------------------+

| Steel              | Single mill-level     | Onboard secondary tier-1 steel mills  |

| (100 delay days)   | production backlogs   | and buy from regional stockyards      |

+--------------------+-----------------------+---------------------------------------+

Sand Mitigation: Replace river sand dependency with local M-Sand (Manufactured Sand) plants, which operate under commercial manufacturing licenses unaffected by seasonal riverbed mining bans.

Plumbing Mitigation: Reallocate purchase orders from Zenith Piping Systems (Rating: 2.5) to established regional distributor networks holding buffered warehouse stock.

Steel Mitigation: Onboard secondary steel suppliers (SAIL, Tata Tiscon, JSW) and buy standard rebar lengths from distributor stockyards rather than waiting for direct mill rolling schedules from Mahavir Steel Corp.

5. Rescheduling & Schedule Optimization Opportunities

Fast-Track Structural Concrete Works: Because Concrete and Aggregates arrive on time without variance, fast-track foundation, slab shuttering, and structural pouring schedules ahead of MEP installations.

Decouple MEP/Finishing Schedules: MEP rough-ins and wall tiling are currently stalled waiting for delayed steel conduits and piping. Re-sequence dry construction, plastering, or exterior cladding works to keep labor productive while plumbing and electrical orders arrive.

Lead-Time Buffer Adjustments: Extend purchase order lead times in the ERP system by 15 days for Sand and 10 days for Steel to reflect vendor realities.

6. Site Staging Clashes & Asymmetric Delivery Impacts

Yes, asymmetric material deliveries are causing site congestion and execution clashes:

Pour Readiness Clashes: Synergy Concrete Co delivers Ready Mix Concrete (RMC) on time, but if rebar steel (Mahavir Steel, delayed 7–9 days) or conduit pipes (Zenith Piping, delayed 11–14 days) are late, concrete pouring cannot take place.

Physical Space Bottlenecks: On-time arrival of bulk aggregates takes up critical laydown space on site. Holding aggregate piles and idle RMC transit mixers while waiting for late steel binding wire or plumbing sleeves causes logistics traffic jams and site disruption.

7. Active & Proposed Countermeasures

[Supplier Tiering]    ---> Shift volumes to 4.5+ rated suppliers (Synergy, Apex)

[Dual Sourcing]      ---> Mandate 70/30 split allocation for Steel & Sand

[Contractual SLAs]   ---> Enforce 0.5%/week Liquidated Damages (LD) for delays

[Pre-Shipment QA]    ---> Third-party factory audits to eliminate 160+ pipe defects

[Payment Incentives] ---> Move critical sand vendors from COD to milestone terms

8. Impact of Uncontrollable / Environmental Factors

UNCONTROLLABLE vs CONTROLLABLE DELAY DAYS

Uncontrollable (Quarry & Weather) : [192 Days - 35.7%]

External Disruptions (Strikes)   : [136 Days - 25.3%]

Vendor Controllable Operations   : [210 Days - 39.0%]

Strictly Uncontrollable / Environmental: 192 Delay Days (35.7%)

Quarry Restrictions: 180 days (33.5%)

Weather Disruptions: 12 days (2.2%)

External Industry Disruptions: 136 Delay Days (25.3%)

Transport Strikes: 111 days (20.6%)

Customs Holds: 25 days (4.6%)

Controllable Vendor Operations: 210 Delay Days (39.0%) (Production backlogs, bad logistics, raw material shortages).

9. Impact of Deploying Extra Manpower & Machinery

+------------------------------------------------------------------------------------+

|                         EXTRA MANPOWER & MACHINERY MATRIX                          |

+------------------------------------+-----------------------------------------------+

| Where Extra Resources WILL Help    | Where Extra Resources WILL NOT Help           |

+------------------------------------+-----------------------------------------------+

| * On-site rebar cutting/bending    | * Quarry mining permit shutdowns              |

|   machinery & dedicated fixers     | * Port/Customs clearance holds                |

| * Automatic aggregate batching     | * Interstate transport/freight strikes        |

| * Mechanized material unloading    | * Mill manufacturing backlogs                 |

+------------------------------------+-----------------------------------------------+

Caution: Deploying extra site labor while materials are stuck at quarries or ports results in unproductive labor headcount overruns. Extra labor should only be mobilized once material arrives at site laydown areas.

10. Financial Friction, Material Shortages & Inventory Deficits

PAYMENT TERMS VS AVERAGE DELAY DAYS

Net 15 (Concrete)      | 0.0 Days

Advance 20% (Tiles)    |=== 2.2 Days

Net 30 (Cement/Pipes)  |====== 4.1 Days

Net 45 (Electrical)    |======= 5.1 Days

Net 60 (Steel)         |============ 7.7 Days

Cash on Delivery (Sand)|==================== 12.2 Days

Material Shortfalls: 28 out of 100 POs experienced partial delivery shortfalls (e.g., receiving 48 tons instead of 50 tons of steel), accumulating a combined deficit of 1,023 physical material units on site.

Payment Terms Friction: Orders under Cash on Delivery (COD) (sand suppliers) suffered the highest average delay (12.2 days/order) and the largest cost overruns (+₹19.34 Lakhs), reflecting spot-market price disputes prior to dispatch.

Credit Terms Correlation: Vendors on predictable structured payment plans (Net 15 or Advance 20%) delivered on-time or with negligible delays, proving that vendor liquidity directly affects supply reliability.